## Cover
| Web Programming Project |  | TEAM 11:
| SCRUM |  | Heidrich, Lorand - Scrum Master
Kaikas, Evangelos - Head of Validation
Kovacs, Daniel - Database Manager
2021 HÄMK
Forum Nightclub
Product Backlog
Sprint Planning
Sprint 1 Backlog
Sprint 2 Backlog
Sprint 3 Backlog
Review
Sprint Retrospective

## Guide
Workflow for scrum practices
Note: Sprint review and retrospective for the last week is done during the demonstration.
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points (next module)
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## Product Backlog
Team 11 Product Backlog
ID | User Story | Story Points Total | Priority
1 | Have a good looking welcome page | 5 | 1
2 | Well organized and succinct pages | 2 | 2
3 | Nice header with hamburger menu, social media links and login | 3 | 1
4 | Footer with links to privacy and terms with hours and contact info | 1 | 1
5 | Bottle service page leading to phone number and tickets page | 3 | 3
6 | Tickets page with form to purchase event tickets | 8 | 3
7 | Viewers should be able to see upcoming events | 2 | 3
8 | About Us page with contact links | 3 | 3
9 | Dress code page | 1 | 4
10 | Careers page with form to submit CV | 6 | 3
11 | Contact Us page with form for customers to reach out | 3 | 3
12 | Users should be able to create an account and login | 6 | 2
13 | Ensure website is reactive | 1 | 1
14 | Perform testing on components | 2 | 1
15
16
17
18
TOTAL |  | 46

## Sprint Planning Meeting
Sprint Planning
Sprint | Participants
Sprint1 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Location: Online | Attended | Attended | Attended
Date: Feb. 10, 21 | Suomi | Greece | Hungary
Sprint 2 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Location: Online | Attended | Attended | Attended
Date: Feb. 17, 21 | Suomi | Greece | Hungary
Sprint 3 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Location: Online | Attended | Attended | Attended
Date: Feb. 24, 21 | Suomi | Greece | Hungary
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## Sprint 1 Backlog
Sprint Backlog : Sprint 1
ID | BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
1 | Design landing page | 1 | ALL | Completed | 1.5 | [5 empty] | Not Started
1 | Create reactive landing page HTML in PHP file with login and social media | 1 | Lorand | Completed | 1.5 | [5 empty] | In Progress
1 | Make pop-out hamburger menu | 2 | Daniel | Completed | 1 | [5 empty] | Completed
1 | Create stylesheet for landing page | 1 | Lorand | Completed |  | 3
2 | Map out how pages are linked together | 1 | ALL | Completed | 0.25
2 | Design pages and their layout | 1 | ALL | Completed | 2
3 | Make header.php file with nav links for social media and login to be included in pages | 1 | Daniel | Completed |  | 1
3 | Make hamburger menu for header | 2 | Lorand | Completed |  |  | 0.25
4 | Make footer with hours, terms, conditions, google-maps link to address, and contacts | 1 | Daniel | Completed |  |  | 1
5 | Create bottle-service.php; include header, footer with own meta tags | 1 | Evangelos | Completed |  |  | 1
5 | Add buttons for phone>>phone no, tickets>>tickets.php, menu>>menu.php | 1 | Evangelos | Completed |  |  | 1
5 | Create menu.php with bottle service menu; include header, footer, own meta tags | 1 | Evangelos | Completed |  |  |  | 1
6 | Create tickets.php page; include header, footer, own meta tags | 1 | Lorand | Completed |  |  |  | 1
6 | Make form for ticket purchase: choose event, enter customer info | 2 | Lorand | Completed |  |  |  |  | 1
6 | Validate tickets form so unauthorized fields are not accepted with JavaScript | 3 | Evangelos | Completed |  |  |  |  | 2
6 | Users should be able to manage their tickets dynamically (CRUD) | 2 | Daniel | Completed |  |  |  |  | 2
7 | Make bootstrap image slider for event flyers listing all current events | 2 | Daniel | Completed |  |  |  |  | 0.5
TOTAL
TOTAL |  |  |  |  | 6.25 | 4 | 3.25 | 2 | 5.5 | 21

## Sprint 2 Backlog
Sprint Backlog : Sprint 2
ID | BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
8 | Create about_us.php; include header, footer, own meta tags | 1 | Evangelos | Completed |  | 1 |  |  |  |  | Not Started
8 | Include reservation info with contact number and link for ticket purchases | 1 | Evangelos | Completed |  |  | 0.5 |  |  |  | In Progress
8 | Include private event info with dedicated link for phone and email | 1 | Evangelos | Completed |  |  |  | 0.5 |  |  | Completed
9 | Create dress_code.php; include header, footer, own meta tags | 1 | Lorand | Completed |  | 1
10 | Create careers.php; include header, footer, own meta tags | 1 | Lorand | Completed |  |  | 1
10 | Make form for applicants to enter info | 2 | Daniel | Completed |  | 1.5
10 | Include attachment for CV and Photo | 1 | Daniel | Completed |  |  | 0.5
10 | Form sends e-mail to dedicated email address | 2 | Lorand | Completed |  |  |  | 1
TOTAL |  |  |  |  | 0 | 3.5 | 2 | 1.5 | 0 | 7

## Sprint 3 Backlog
Sprint Backlog : Sprint 3
ID | BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
11 | Create contact_us.php; include header, footer and own meta tags | 1 | Lorand | Completed | 1 | [5 empty] | Not Started
11 | Send message to designated contact email | 2 | Lorand | Completed | 0.5 | [5 empty] | In Progress
12 | Make entire page login accessible | 3 | Daniel | Completed | 4 | [5 empty] | Completed
12 | Create login popup form | 1 | Evangelos | Completed | 1
12 | Validate login form to check for unwanted elements or blanks | 2 | Evangelos | Completed | 1
13 | Test website to ensure fully reactive | 1 | Lorand | Completed |  | 1
14 | Test dynamic components | 1 | Evangelos | Completed |  | 1
14 | Test CRUD components | 1 | Daniel | Completed |  | 1
TOTAL |  |  |  |  | 7.5 | 3 | 0 | 0 | 0 | 10.5

## Sprint Review
Sprint Review
Sprint | Participants
Sprint 1 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Online | Online | Online | Online
Sprint 2 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Online
Sprint 3 | Daniel Kovacs | Evangelos Kaikas | Lorand Heidrich
Online
Team presents what it accomplished during the sprint
Typically takes the form of a demo of new features or underlying architecture
Informal
2-hour prep time rule
No slides
Whole team participates
Invite the world
Summary of the meeting that includes decisions you made.
Sprint 1: Sprint planning: Completed successfully as a team. Tasks were distributed based on selection, dividing the 5 user stories into 4 tasks each.
Daily sprints: Scrum master Oluwole made sure daily sprints were 15 minutes maximum. Next user story tasks were chosen at the end of daily sprints and documented in Meeting Minutes along with completed tasks.
Sprint review: Teamwork has been presented, corrections have been applied based on user story requirements.
Sprint retrospective: All teammates were punctual regarding sprint meeting attendance. Tasks were completed on schedule. Sprint accomplished on schedule. Started 30 Nov 2020, finished 4 Dec 2020.
Sprint is signed off, next sprint begins Monday 7 Dec, 2020.
Sprint Planning Meeting: 16:00 EET
Location: Online

## Retrospective
Just discuss in your team, no documentation required
Sprint retrospective
Periodically take a look at what is and is not working
Typically 15–30 minutes
Done after every sprint
Whole team participates
ScrumMaster
Product owner
Team
Possibly customers and others